## Time_line
			Project reference:	2023.15110.PEX
			Project title:	Induction of Stochastic Answer Set Programs by Algebraic Means
Tasks
Task Id	Designation	Person * month	Participant responsible for task	Acronyms of partners involved in task	Months
					1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18
					set 24	out 24	nov 24	dez 24	jan 25	fev 25	mar 25	abr 25	mai 25	jun 25	jul 25	ago 25	set 25	out 25	nov 25	dez 25	jan 26	fev 26
1	Structure and Induction of SASP (SI)	5,00	Francisco Coelho	UÉ	1	2	3	4	5	6	7	8	9	10	11	12
2	Integration of SASP with existing ASP and ILP software frameworks (INT)	14,00	Francisco Coelho	UÉ				1	2	3	4	5	6	7	8	9	10	11	12
3	Applications of SASP (APP)	4,00	Francisco Coelho	UÉ; HPCC					1	2	3	4	5	6	7	8	9	10	11	12
		23,00
Milestones									SI Paper 1					SI Paper 2
									INT Report					INT Paper
									APP Report					APP Paper